## Status Report 8-27
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-27 | Overall Status: | Yellow
Contact: | Joe McAdams | Explanation: | Not able to start, still working on assessment.
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
API chosen, approved and general idea of what to do with that API planned.
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 0% | 2021-08-28
API Testing |  | 0% | 2021-08-28
Back-end |  | 0% | 2021-08-30
Business logic |  | 0% | 2021-08-30
Front-end |  | 0% | 2021-08-31
Testing |  | 0% | 2021-09-01
Presentation |  | 0% | 2021-09-02
Reviewing requirements |  | 0% | 2021-09-02

## Status Report 8-30
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-30 | Overall Status: | Green
Contact: | Joe McAdams | Explanation:
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
API chosen, approved and general idea of what to do with that API planned.
Environment set up, project skeleton built, API querying tested with RestTemplate
Landing page created with buttons and background
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% | 2021-08-28
API Testing |  | 100% | 2021-08-28
Back-end |  | 0% | 2021-08-31
Business logic |  | 0% | 2021-08-31
Front-end |  | 20% | 2021-08-31
Testing |  | 0% | 2021-09-01
Presentation |  | 0% | 2021-09-02
Reviewing requirements |  | 0% | 2021-09-02

## Status Report 8-31
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-31 | Overall Status: | Green
Contact: | Joe McAdams | Explanation:
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
All entities related to the PokeAPI created and any query made using RestTemplate successfully auto-populates all related fields
Able to search for any pokemon by name and display its assosciated data on an info page
Set backgrounds and borders for a cleaner looking website
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% | 2021-08-28
API Testing |  | 100% | 2021-08-28
Back-end |  | 50% | 2021-08-31 | All entities for API queries created
Display info logic |  | 90% | 2021-08-31
Battle logic |  | 5% | 2021-08-31
Front-end |  | 40% | 2021-08-31
Testing |  | 0% | 2021-09-01
Presentation |  | 0% | 2021-09-02
Reviewing requirements |  | 0% | 2021-09-02

## Status Report 9-1
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-31 | Overall Status: | Green
Contact: | Joe McAdams | Explanation:
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Added teams feature: able to create a team and add pokemon to it by name.
Implemented back end DAOs and service layers to accomplish team creation/viewing
Implemented ability to delete teams and their assosciations
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% | 2021-08-28
API Testing |  | 100% | 2021-08-28
Back-end |  | 75% | 2021-09-01 | Teams saved/retrieved/deleted from database
Display info logic |  | 100% | 2021-08-31
Battle logic |  | 5% | 2021-09-01
Front-end |  | 70% | 2021-09-01
Presentation |  | 0% | 2021-09-02
Reviewing requirements |  | 0% | 2021-09-02

## Status Report 9-2
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-31 | Overall Status: | Green
Contact: | Joe McAdams | Explanation:
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Added team battle feature
All features implemented along with (somewhat) nice styling and cleanliness
Added some input validation
ID # | Key Issues | Action Plan |  |  | Status
1 | Input validation | Validate input! |  |  | Incomplete
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% | 2021-08-28
API Testing |  | 100% | 2021-08-28
Back-end |  | 100% | 2021-09-01
Display info logic |  | 100% | 2021-08-31
Battle logic |  | 95% | 2021-09-01
Front-end |  | 95% | 2021-09-01
Presentation |  | 0% | 2021-09-02
Reviewing requirements |  | 100% | 2021-09-02

## Status Report 9-3
Status Report for Joe McAdams - Pokemon API Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-31 | Overall Status: | Green
Contact: | Joe McAdams | Explanation:
Prepared By: | Joe McAdams
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Everything is done and I've completed my presentation!
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100% | 2021-08-28
API Testing |  | 100% | 2021-08-28
Back-end |  | 100% | 2021-09-01
Display info logic |  | 100% | 2021-08-31
Battle logic |  | 100% | 2021-09-01
Front-end |  | 100% | 2021-09-01
Presentation |  | 100% | 2021-09-02
Reviewing requirements |  | 100% | 2021-09-02